## Backlog
Ticket ID | Epic | Day | Title | Description | Acceptance Criteria | Primary Assignee | Support / Pairing | Est Hours | Priority | Dependencies | Status
INF-01 | Foundation | D1 | Repo, CI/CD & environments | Set up monorepo, lint/test CI pipeline, staging + production environments on a stack the team already knows. | Push to main auto-deploys to staging; staging URL reachable by whole team. | Tino Britty | - | 4 | Must | - | Not started
INF-02 | Foundation | D1 | Core DB schema & migrations | Create tables for users, institutions, companies, batches, skills, skill claims, verification attempts, projects, project reports, jobs, applications, ATS stages, cognitive/comm profiles, audit logs, plans, feature flags. | Migrations run cleanly on staging; schema matches PRD Section 11 entity list. | Tino Britty | Vishal V | 5 | Must | INF-01 | Not started
INF-03 | Foundation | D1 | Auth skeleton (email/password, role guards) - SSO stubbed | Basic session auth for all 4 roles with route guards per role. Real Entra ID / Google SSO explicitly deferred past this sprint. | Login/logout works per role; protected routes redirect unauthenticated users; role mismatch blocked. | Vishal V | Tino Britty | 5 | Must | INF-02 | Not started
INF-04 | Foundation | D1 | Shared UI component kit | Build the reusable components from the UI Design Brief: verification badge (5 states), AI explanation panel, pipeline/funnel stage bar, candidate profile card shell. | All 4 components exist as reusable, documented components; used verbatim (not re-built) by every downstream screen. | Satheshwaran | - | 5 | Must | - | Not started
INF-05 | Foundation | D1 | Seed taxonomy - Software & IT domain + 15 skills | Seed one domain with ~15 skills and proficiency thresholds per PRD 7.3 (Beginner/Intermediate/Advanced pass bars). | Taxonomy queryable via API; every skill has a defined pass threshold per level. | Vedika Gowda | Ramansh | 5 | Must | INF-02 | Not started
INF-06 | Foundation | D1-D2 | Seed MCQ question bank (Beginner) | LLM-assisted generation + human review of 10 questions per skill for the 10 highest-priority skills (Beginner level only this sprint). | 100 reviewed, tagged questions stored and linkable to a skill + level. | Vedika Gowda | Ramansh | 6 | Must | INF-05 | Not started
SA-T01 | Super Admin | D2 | Institutions CRUD (API + UI) | Create/read/update/deactivate institution accounts. Soft-delete only. | Deactivating an institution locks student logins without deleting data; list/detail/edit all functional. | Vishal V | Satheshwaran | 6 | Must | INF-03 | Not started
SA-T02 | Super Admin | D2 | Companies CRUD (API + UI) | Mirror of Institutions CRUD, plus sector/mode/size fields per PRD SA-09. | Same acceptance pattern as SA-T01, with domain/sector/mode fields present. | Vishal V | Satheshwaran | 6 | Must | INF-03 | Not started
SA-T03 | Super Admin | D2 | Self-onboarding verification queue | Approve/reject self-signed-up institutions and companies with a mandatory reason field. Approving a company unlocks its Pro plan (corrected per PRD SA-11). | Approve/reject both flows work; rejection requires a reason; approval flips plan tier. | Vishal V | - | 4 | Must | SA-T01, SA-T02 | Not started
SA-T04 | Super Admin | D3 | Pricing plan & feature-flag matrix | Simple Free/Basic/Pro toggle matrix per tenant - boolean flags only, no billing/payment integration this sprint. | Toggling a flag for one tenant does not affect others; flags are readable by the app layer. | Vishal V | - | 4 | Must | SA-T03 | Not started
SA-T05 | Super Admin | D2-D3 | Audit log capture + viewer | Log every candidate-profile view and admin verification decision with actor, action, reason, timestamp. | Every SA-T06 profile view produces exactly one audit row; log is searchable/filterable. | Tino Britty | Vishal V | 4 | Must | INF-03 | Not started
SA-T06 | Super Admin | D3 | Candidate profile viewer (reason-code gated) | Brief read-only candidate view for Super Admin. Cannot open without entering a reason code. | No reason code = no access; access is logged via SA-T05. | Vishal V | - | 3 | Must | SA-T05 | Not started
SA-T07 | Super Admin | D4 | Super Admin dashboard | Metric cards, verification queue widget, plan distribution, recent audit feed - per the wireframe already shared. | Dashboard reflects live data from SA-T01 through SA-T06, no dummy numbers left in. | Vishal V | Satheshwaran | 5 | Must | SA-T01..SA-T06 | Not started
AC-T01 | Academia | D2 | Batch management CRUD | Create/edit batches, assign a domain/department, map students into a batch. | A TPO can create a batch and assign 1+ students to it. | Vedika Gowda | Vishal Bharath | 4 | Must | INF-03 | Not started
AC-T02 | Academia | D2 | Candidate bulk provisioning | CSV/Excel upload with column mapping, invite preview, and send-invites action. | Uploading a well-formed CSV creates N candidate accounts and sends N invite emails; malformed rows are reported, not silently dropped. | Vedika Gowda | Vishal Bharath | 5 | Must | AC-T01 | Not started
AC-T03 | Academia | D3 | JD inbox | List incoming JDs from companies with status (New/Matching/Shortlisting/Sent). | New JD from CO-T01 appears here within one refresh cycle. | Vishal Bharath | - | 3 | Must | CO-T01 | Not started
AC-T04 | Academia | D3-D4 | Ranked candidate suggestions | Consume the Matching Engine (SE-T05) output and show a ranked list per JD with a one-line match explanation. | Every suggested candidate shows a score and a plain-language reason. | Vishal Bharath | Satheshwaran | 5 | Must | SE-T05 | Not started
AC-T05 | Academia | D4 | Shortlist & send-opportunity flow | TPO shortlists candidates from AC-T04; shortlisted candidates receive an in-app opportunity notification. | Shortlisting triggers a notification (SE-T07) to the candidate and creates an Application record. | Vishal Bharath | Satheshwaran | 5 | Must | AC-T04 | Not started
AC-T06 | Academia | D4 | Confidence-score review & send-to-company | TPO reviews the AI confidence-interview score (SE-T02) per candidate and sends the final shortlist to the company. | Sending updates the Application status and creates entries in the company's ATS (CO-T02). | Vishal Bharath | - | 4 | Must | SE-T02 | Not started
AC-T07 | Academia | D4 | Academia dashboard | Profile completion, skill verification snapshot, placement pipeline bar, batch readiness, skill-gap list - per wireframe already shared. | Dashboard reflects live data from AC-T01 through AC-T06. | Vishal Bharath | Satheshwaran | 6 | Must | AC-T01..AC-T06 | Not started
CN-T01 | Candidate | D2 | Onboarding wizard | Forced password reset, resume upload trigger, mandatory profile fields, DPDP-aligned consent screens, completion gate. | Candidate cannot reach the dashboard until all mandatory fields + consent are complete. | Satheshwaran | Vishal Bharath | 8 | Must | INF-04 | Not started
CN-T02 | Candidate | D2 | Resume upload + AI parse pre-fill | Use an LLM to extract structured fields (education, experience, skills) from the uploaded resume and pre-fill the form. | At least 70% of extractable fields are correctly pre-filled on a sample of 5 test resumes; manual edit always possible. | Ramansh | Vishal Bharath | 5 | Must | CN-T01 | Not started
CN-T03 | Candidate | D2 | Profile - education / experience / languages | Standard CRUD sections plus language + fluency picker. | All fields save and reload correctly; validation on required fields. | Vedika Gowda | Vishal Bharath | 5 | Must | CN-T01 | Not started
CN-T04 | Candidate | D2-D3 | Profile - skills section | Domain-scoped skill picker (from INF-05 taxonomy) with proficiency selector and a live status badge per skill (Declared/In verification/Verified/Locked+cooldown date). | Declaring a skill immediately shows 'Declared' status and queues verification (SE-T01). | Satheshwaran | Vishal Bharath | 5 | Must | INF-05 | Not started
CN-T05 | Candidate | D3 | Candidate dashboard | Profile completion, verified skill chips, upcoming items, application tracker preview, public-profile card - per wireframe already shared. | Dashboard reflects live data, no placeholder numbers. | Satheshwaran | - | 5 | Must | CN-T01..CN-T04 | Not started
CN-T06 | Candidate | D4 | My Applications tracker | List + status timeline that mirrors the company's ATS stage in real time. | Changing a stage in CO-T02 updates this screen without a manual refresh needed beyond standard polling. | Vishal Bharath | Satheshwaran | 4 | Must | CO-T05 | Not started
CN-T07 | Candidate | D4 | Public profile page | Shareable, view-only page with candidate-controlled section visibility toggles, embedded project videos, verified badges. | Toggling a section off on the private profile hides it on the public URL immediately. | Satheshwaran | - | 5 | Must | CN-T04, SE-T03 | Not started
CN-T08 | Candidate | D3 | Project submission form | Template-driven form (problem/approach/stack/outcome) with a Loom link field and optional GitHub link field. | Submitting queues SE-T03 and shows a 'processing' state, not a silent spinner. | Satheshwaran | Vishal Bharath | 5 | Must | CN-T04 | Not started
SE-T01 | Shared Engine | D3 | Skill verification state machine + Beginner MCQ runner | Implement the 2-strike/cooldown state machine from PRD 7.3: Declared -> Verified / Demoted -> Beginner reattempt -> Verified-Beginner / Locked -> Cooldown. | State transitions match the PRD table exactly, including the cooldown date calculation. | Ramansh | Vishal Bharath | 8 | Must | INF-06, CN-T04 | Not started
SE-T02 | Shared Engine | D3-D4 | AI confidence / skill interview | LLM generates skill-relevant questions, scores the candidate's typed or transcribed response, returns pass/fail plus a one-line explanation. | Every result includes a visible 'why' explanation, not just a score. | Ramansh | - | 8 | Must | SE-T01 | Not started
SE-T03 | Shared Engine | D3-D4 | Project verification AI agent | Calls GitHub API to read repo structure/README, feeds to LLM for relevance/quality scoring, applies a basic duplicate-text heuristic. Low-confidence results route to a human-review flag rather than auto-rejecting. | Every submission produces a report with a score, flags, and a review-queue entry when confidence is low. | Ramansh | - | 8 | Must | CN-T08 | Not started
SE-T04 | Shared Engine | D4 | Cognitive & communication profiling | One autonomous LLM-generated strengths/weaknesses narrative, independent of any specific skill claim. | Every onboarded candidate has a narrative generated within this sprint's demo dataset. | Ramansh | - | 5 | Must | CN-T01 | Not started
SE-T05 | Shared Engine | D3 | Matching engine (rules-based) | Weighted score = skill match + proficiency met/exceeded + domain match + experience relevance. | Given a JD and a candidate pool, produces a ranked list with a numeric score for each candidate. | Vishal V | - | 5 | Must | INF-05, CO-T01 | Not started
SE-T06 | Shared Engine | D4 | Proctoring-lite (STUBBED - not full liveness/ID verification) | Webcam permission + periodic snapshot capture + tab-blur/window-switch event logging only. Full ID/liveness vendor integration explicitly out of scope this sprint. | Snapshot and tab-blur events are captured and stored against the session; clearly labeled in-app as a lite version. | Satheshwaran | Tino Britty | 5 | Must | SE-T01 | Not started
SE-T07 | Shared Engine | D3 | Notification service | Email + in-app notifications for opportunity, status change, and verification results. | Triggering events (shortlist, stage change, verification result) reliably produce a notification. | Vishal V | - | 4 | Must | INF-03 | Not started
CO-T01 | Company | D3 | JD posting form + list | Structured JD form: domain, required skills with minimum proficiency, experience range, location, employment type, headcount. | Required skills must be picked from the taxonomy (INF-05), not free text. | Vishal Bharath | Satheshwaran | 5 | Must | INF-03 | Not started
CO-T02 | Company | D3-D4 | ATS Kanban board | Drag-and-drop stages: New Matches -> Shortlisted -> AI-Verified -> Interviewing -> Offer -> Hired/Rejected. | Dragging a card updates its stage and triggers CO-T05 sync. | Vishal Bharath | Satheshwaran | 6 | Must | CO-T01 | Not started
CO-T03 | Company | D4 | Candidate profile card (read-only) | Verified badges, cognitive/comm summary, embedded project videos. No download or export affordance. | No UI element allows exporting or copying raw candidate data in bulk. | Satheshwaran | - | 3 | Must | CN-T04, SE-T03 | Not started
CO-T04 | Company | D4 | Company dashboard | Active openings, new matches, pipeline overview, recent matches list - per wireframe already shared. | Dashboard reflects live data from CO-T01/CO-T02. | Tino Britty | Satheshwaran, Vishal Bharath | 4 | Must | CO-T02 | Not started
CO-T05 | Company | D4 | Status sync - ATS stage -> candidate status | Stage changes in CO-T02 propagate to the candidate's My Applications view (CN-T06). | Change is visible to the candidate within one polling cycle. | Tino Britty | Vishal V | 3 | Must | CO-T02, CN-T06 | Not started
QA-T01 | Release | D5 | End-to-end flow test | Walk the full loop: candidate onboarding -> skill verification -> project submission -> TPO shortlist -> AI confidence interview -> company ATS -> hire, on one seeded test dataset. | All four roles complete their part of the loop without a manual DB fix required. | Tino Britty | All | 6 | Must | All above | Not started
QA-T02 | Release | D5 | Bug bash & fixes | Whole team tests each other's modules and fixes anything blocking the demo flow. | No P0/P1 bug open against the demo script by end of day. | All | - | 6 | Must | QA-T01 | Not started
QA-T03 | Release | D5 | Staging -> production deploy | Cut the release and deploy to production. | Production URL passes the same walkthrough as staging. | Tino Britty | - | 3 | Must | QA-T02 | Not started
QA-T04 | Release | D5 | Demo script & handoff doc | One-page script covering the four-role demo, plus a note of every stubbed/simulated component for stakeholders. | Anyone on the team could run the demo cold from this doc. | Tino Britty | Vishal V | 3 | Must | QA-T03 | Not started

## Capacity Check
Team member | Role | Primary-owned hours (this sprint) | Weekly budget (5 x 8h) | Remaining / (Over)
Tino Britty | System Architect & Production (Expert) | 32 | 40 | 8
Vishal V | Backend Engineer (Expert) | 42 | 40 | -2
Vishal Bharath | Full Stack Engineer - Backend-leaning | 38 | 40 | 2
Satheshwaran | Full Stack Engineer - Frontend-leaning | 41 | 40 | -1
Ramansh | AI Engineer (Intermediate) | 34 | 40 | 6
Vedika Gowda | Data Ops Engineer (Beginner/Intern) | 25 | 40 | 15
Note: totals count each ticket's Primary Assignee only. Support/pairing hours are collaboration time on top of this and are not separately summed here.
QA-T02 (Bug bash, 6h, assignee 'All') is a whole-team activity and is intentionally excluded from individual totals.

## Scope Cuts (Deferred)
Area | What the PRD V1 describes | What this 1-week sprint actually ships | Why
SSO | Microsoft Entra ID (Academia), Google Workspace + Microsoft (Company) | Email/password auth only, pluggable auth layer left ready for SSO | Enterprise SSO app registration + admin-consent flows take days of vendor/tenant setup, not hours
Proctoring | Full pre-check (ID + liveness match, environment scan, mic calibration), continuous face/gaze tracking, multi-person detection | Webcam snapshot + tab-blur/window-switch logging only - explicitly labeled 'lite' in-app | Liveness/ID verification is a vendor integration with contracts and compliance review; cannot be built safely in days
Project plagiarism check | Compare against public repos and prior submissions at scale | Basic duplicate-text heuristic + LLM relevance/quality scoring, human-review queue for anything uncertain | A real plagiarism corpus/index is a multi-week data engineering effort
Taxonomy breadth | Domain taxonomy versioned and expandable across all engineering sub-domains | One domain seeded (Software & IT), ~15 skills, Beginner-level question bank only | Content authoring at full breadth is a content-ops workstream, not a code workstream
Multi-tenancy isolation | Fully isolated multi-tenant data architecture | Shared DB with tenant_id scoping enforced at the API layer | Full isolation (separate schemas/DBs per tenant) is a hardening pass, not needed to prove the loop works
Compliance exports, NAAC/NBA | Already V2 in the PRD | Not built | Confirmed out of scope - no change
Assessment/Interview builder (TPO) | Already V2 in the PRD | Not built | Confirmed out of scope - no change
Multi-seat company accounts | Already V2 in the PRD | Not built | Confirmed out of scope - no change